{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["Sheet1"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":18,"n_cols":82,"rows_kept":18,"cut":false,"hidden":false,"merged":[]}
[]
[null,null,32,{"$nulls":17},4,{"$nulls":30},5]
[null,null,14,15,16,17,18,19,20,21,22,23,24,25,26,27,28,29,30,31,1,2,3,4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22,23,24,25,26,27,28,29,30,31,1,2,3,4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22,23,24,25,26,27,28,29,30,31]
["분석","업무분석/DB분석(완료)"]
[null,"기획분석"]
["설계","페이지 설계"]
["개발","개별 페이지 구현"]
["개발","개별 페이지 테스트"]
[null,"결제/사인패드/프린터연동"]
[null,"결제 테스트"]
[]
[]
[null,"4차 검수"]
[]
[null,"5차 검수"]
[null,"완료"]
[null,"진행"]
[null,"예정"]